**PROJECT PLAN**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT NAME | E-Recruitment System (Online Job Portal) | | | PROJECT MANAGER | Abdul Rehman |
| PROJECT DELIVERABLE | 20 January 2021 | | | | |
| SCOPE STATEMENT | This product will use all over the world by both Job Seekers and agencies for free of cost. | | | | |
| START DATE | 01/10/2020 | END DATE | 20/01/2021 | OVERALL PROGRESS | 30% |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **AT RISK** | **TASK NAME** | **ASSIGNED TO** | **START  DATE** | **END  DATE** | **DURATION**  in days | **STATUS** |
| **1** | Requirement Analysis | Team | 01/10/20 | 14/10/20 | 14 | complete |
| **1.1** | Project Proposal | Team | 01/10/20 | 07/10/20 | 7 | complete |
| **1.2** | SRS Form | Team | 08/10/20 | 14/10/20 | 7 | In Progress |
| **2** | Design Phase | Team | 15/10/20 | 06/11/20 | 21 | complete |
| **2.1** | Class Diagram | Team | 15/10/20 | 21/10/20 | 7 | complete |
| **2.2** | ERD Diagram | Team | 22/10/20 | 28/10/20 | 7 | complete |
| **2.3** | Wireframes | Team | 29/10/20 | 06/11/20 | 7 | complete |
| **3** | Front End Development | Team | 06/11/20 | 20/11/20 | 14 | complete |
| **4** | Back-End Development | Team | 21/11/20 | 18/12/20 | 28 | In Progress |
| **5** | Testing | Team | 18/12/20 | 02/01/21 | 14 | In Progress |
| **5.1** | Test Case Writing | Team | 18/12/20 | 25/12/20 | 7 | In Progress |
| **5.2** | Backlog Forms | Team | 25/12/20 | 02/01/21 | 7 | In Progress |
| **6** | Deployment | Team | 02/01/21 | 17/01/20 | 15 | In Progress |

|  |
| --- |
| **DISCLAIMER**  Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk. |